## Sheet1
TOWN OFFICE SOLUTION PROPOSALS: 2006-2016
|  |  | TOWN HALL RELATED SOLUTION - (Entire Project) | TOWN HALL RELATED SOLUTION - (Partial) | OTHER SOLUTIONS | USE OF BACC
| PROPOSAL | DATE CONSIDERED | PROPOSED COST | OUTCOME | % in favor | % not in favor
1 | Purchase and renovation of Valley Transportation land & buildings (now Valley Fire on Rt. 114) for town facilities and to build a salt shed | MARCH 15, 2006 | $2,800,000 (bond) | Yes- 128, No- 160 Article Did Not Carry | 44.4% | 55.6%
2 | Renovation of Town Hall building to include town offices, sprinklers throughout and elevator access to the second floor, construction of a new police station, highway garage, and salt shed (Note: the new buildings were proposed for the lower portion of the transfer station lot) | MARCH 13, 2007 | $3,500,000 (bond) | Yes- 150, No- 118, Article Did Not Carry | 56% | 44%
3 | Article 41. To see if the Town of Bradford will vote to maintain the status, mission and operation of the Bradford Area Community Center as a taxpayer maintained building steered by a Governance board comprised of citizens, that building to provide space and social, recreation and educational programs for not-for-profit organizations, community groups, children, youth, families and older adults in the greater Bradford area. That the usage and development of the Bradford Area Community Center continue to be designated as an intergenerational community center that provides needed educational, social, medical, and human services to ALL individuals and their families in the greater Bradford Area and more specifically, that the Bradford Area Community Center available space not be permanently occupied, used or leased to for profit agencies, businesses or others that do not fit into said mission of the Bradford Area Community Center. BY PETITION | MARCH 8, 2011 | N/A | Article Carried (Note: The town offices were moved from the Town Hall to the BACC in November 2011.)
4a. | Article Four. To see if the Town will vote to raise and appropriate One Million Seven Hundred Sixty Seven Thousand Dollars ($1,767,000.00) (gross budget) to renovate the Bradford Town Hall at map 16 lot 92 and to authorize the issuance of not more than One Million Seven Hundred Sixty Seven Thousand Dollars ($1,767,000.00) of bonds or notes in accordance with the provisions of the Municipal Finance Act (RSA Chapter 33) and to authorize the Selectmen to issue and negotiate such bonds or notes and to determine the rate of interest thereon, the term and other details. Selectmen recommend. Budget Committee recommends. (2/3 ballot vote required) (passage of this article will not impact the tax rate until 2014) | MARCH 12, 2013 | $1,767,000 (bond) | Yes- 195, No-113 Article Did Not Carry | 63.3% | 36.7%
5 | Article Seven. To see if the Town will vote to authorize the Board of Selectmen to enter into a Five Year lease/purchase agreement to acquire Bradford Corners Map3 Lot 103,103 – A to be used for town office space for the amount of Six Hundred and Fifty Thousand Dollars ($650,000.00). In addition, to vote to raise and appropriate One Hundred Thirty Eight Thousand Four Hundred Fifty Dollars ($138,450.00) for the first year payment. This payment would be funded from Thirty One Thousand Dollars ($31,000.00) in rents with the remaining One Hundred Seven Thousand Four Hundred Fifty Dollars ($107,450.00) to be raised by taxation. This lease has a non-funding clause. (BY PETITION) Majority vote required. Selectmen do not recommend. Budget Committee does not recommend.’ | MARCH 12, 2013 | 650000 | Yes- 30, No-162 Article Did Not Carry | 15.6% | 84.4%
4b. | April 11, 2013 – Special TM to Reconsider vote of March 12 | APRIL 11, 2013 | $1,767,000 (bond) | Yes- 228, No- 224, Article Did Not Carry | 50.4% | 49.6%
Article 4. To see if the town will vote to raise and appropriate One Million Seven Hundred Sixty Seven Thousand Dollars ($ 1,767,000.00) (gross budget) to renovate the Bradford Town Hall at map 16 lot 92 and to authorize the issuance of not more than One Million Seven Hundred Sixty Seven Thousand ($1,767,000.00) of bonds or notes in accordance with the provisions of the Municipal Finance Act (RSA Chapter 33) and to authorize the Selectmen to issue and negotiate such bonds or notes and to determine the rate of interest thereon, the term and other details. Selectmen recommend. Budget Committee recommends. (2/3 ballot vote required)
6 | Article Seven. To see if the Town will vote to raise and appropriate One Million Four Hundred Sixty Six Thousand Dollars ($1,466,000.00) (gross budget) to renovate the Bradford Town Hall at map 16 lot 92 and to authorize the issuance of not more than One Million Three Hundred Thousand Dollars ($1,300,000.00) of bonds or notes in accordance with the provisions of the Municipal Finance Act (RSA Chapter 33.) Further to authorize the Selectmen to issue and negotiate such bonds or notes, to determine the rate of interest thereon, the term and other details. The balance of One Hundred Sixty Six Thousand Dollars ($166,000.00) will be raised from donations and grants. With work proceeding as commitments are made. Selectmen recommends. Budget Committee recommends. (2/3 ballot vote required) (passage of this article will not impact the tax rate until 2015) | MARCH 12, 2014 | $1,300,000 (bond) | Yes- 151, No-88 Article Did Not Carry | 63.2% | 36.8%
Note: The Bradford Board of Selectmen expects to complete the entire project in 2015. All additional work; to include the second floor, paving the parking lot, finishing the basement, finishing the southwest office/room on the 1st floor, and incidentals; will be paid for by grants and donations. No additional tax funds will be used.
7 | Article 9. To see if the town will vote to raise and appropriate the sum of Ninety Five Thousand Dollars ($95,000) to replace the roofing on the Bradford Town Hall (map 16 lot 92) and to cover preconstruction costs associated with the renovation of the Bradford Town Hall. This will be a non-lapsing appropriation per RSA 32:7, VI and will continue until the money is spent or December 31, 2019. If the bond article (Warrant Article Seven) passes this article will be passed over. Selectmen recommended. Budget Committee recommends. | MARCH 12, 2014 | 95000 | Article Carried
8 | Article Three. To see if the Town will vote to raise and appropriate Nine Hundred Fifty Five Thousand Dollars ($955,000.00) (gross budget) to renovate the Bradford Town Hall at map 16 lot 92 including a full workable foundation and to authorize the issuance of not more than Eight Hundred Fifty Thousand Dollars ($850,000.00) of bonds or notes in accordance with the provisions of the Municipal Finance Act (RSA Chapter 33). Further to authorize the Selectmen to issue and negotiate such bonds or notes, to determine the rate of interest thereon, the term and other details. The balance of One Hundred Five Thousand Dollars ($105,000.00) will be raised from donations and grants (currently awarded $105,000 from LCHIP), with work proceeding as commitments are made. Selectmen recommend. Budget Committee recommends. (2/3 ballot vote required) (passage of this article will not impact the tax rate until 2016) | MARCH 15, 2015 | $850,000 (bond) | Yes- 144, No-79 Article Did Not Carry | 64.6% | 35.4%
9 | Selectman John Pfeifle put forth the idea to purchase the former Bruss Construction Office building for the purpose of relocating town offices there. | 2015 | $250,000-$300,000 (estimate), plus any needed retrofittings for the building, and move-in costs | N/A | N/A | N/A
10 | Article Three. To see if the town will vote to raise and appropriate the sum of One Million Three Hundred Thousand Dollars ($1,300,000.00) (gross budget) for the renovation and restoration of the Historic Town Hall at Map 16 Lot 92. The project will provide a full basement, completely operational first floor for town offices and meeting rooms, and a functional second floor. Further to authorize the issuance of not more than Nine Hundred and Seventy Five Thousand Dollars ($975,000.00) of bonds or notes in accordance with the provisions of the Municipal Finance Act (RSA Chapter 33). Further to authorize the Selectmen to issue and negotiate such bonds or notes, to determine the rate of interest thereon, the term and other details. The balance of Three Hundred and Twenty Five Thousand Dollars ($325,000.00) will be raised from donations and grants. The following are funds currently dedicated to offset this balance: | MARCH 9, 2016 | $975,000 (bond) | TBD | TBD | TBD
· $105,000 LCHIP Grant.
· $70,700 Cash and In-Kind donations.
The Selectmen recommends. Budget Committee recommends. (2/3 ballot vote required)
11 | Article Six. To see if the town will vote to raise and apporpriate the sum of Ninety five Thousand Dollars ($95,000) to be placed in the Town Hall Repair and Restoration Trust Fund (established in 2013) for the continuing renovation of the Bradford Historic Town Hall. This article will be withdrawn with the passge of the Town Hall Bond iisue. BY PETITION. | MARCH 9, 2016 | 95000 | TBD | TBD | TBD
12 | Article Seven. To see if the town will vote to raise and appropriate the sum of Thirty Thousand Dollars ($30,000) to relocate the town offices into the Town Hall and to withdraw Thirty Thousand dollars ($30,000) from the Town Facilities Capital reserve for this purpose. No new money will be raised by taxation. This will be a non lapsing appropriation and continue until December 31, 2021. This warrant will be withdrawn if the Town Hall bond article passes. | MARCH 9, 2016 | Withdrawal of $30,000 from Town Facilities Cap Reserve | TBD | TBD | TBD