## Sheet1
Town Hall warrant article for March 2017 Town Meeting - pricing
Item | $ | Bidder
Lift building, dig out underneath and lower building | 127000 | Bid in hand
Remove material dug out | 0 | Bradford Hwy Dept
Pour footings, basement floor and walls | 117000 | Bid in hand
Sprinkler system (1) | 187000 | Bid in hand
Electrical, including alarm system (1) | 90000 | Estimate
LP hot water heating system (1) wo/ac | 70000 | Bid in hand
Plumbing as necessary after lift | 10000 | Estimate probably high
Carpentry includes 2nd floor windows | 83000 | Conservative estimate
Vault | 0 | Probably not to be constructed
Exterior wall blown in cellulose insulation. Basement incl. | 17610 | Includes foundation sealing
Exterior Paint and trim repair | 34000 | Bid in hand; Another bid coming
Clerk of Works | 33000 | Already identified
Architectural costs additional specifications estimate | 16000 | Estimate
Waste removal | 4000 | Estimate
Miscellaneous/contingency | 72390 | Slightly less than 10%
(1) Complete 1st floor, roughed in for 2nd floor.
Total | 861000
GRANTS AND CONTRIBUTIONS IN HAND | 186000
BOND AMOUNT | 675000 | BOND AMOUNT $675,000 AS APPROVED BY THROC ON 2/8/2017
BLS REV 2/9/2017